## Tracking Spreadsheet
Tenant Transition Plan - To be completed and updated throughout project.
Project Name |  |  | Project Address(s) | [5 empty] | Report Date
***** APARTMENTS TENANT TRANSITION PLAN AND RELOCATION TRACKER | [5 empty] | This report should be updated and submitted monthly to NDHFA.
Tenant Rent Roll Listing and URA Tracking and Outcomes | [5 empty] | DATE of ION | [21 empty] | Retain supplementary documentation of all incurred costs (e.g. invoices, proofs of payments, HUD reimbursement request form, cost estimates for moving companies, etc.)
Unit # | Status | Tenant Name | Unit Type #BR, # Bath/ Sq Ft | # Persons in Household | Lease Start Date | Lease End Date | Household Income | Income Qualified to return to unit? | Low Income Qualified? Sec 104(d) | Rent Per Month | Tenant Utility Payment | Tenant Portion of Rent | Racial/Ethnic Code | GIN Delivery Date | GIN Method of Delivery | Legal Status Confirmed | Tenant Status Displaced or Non-Displaced | Temp. Relocation Required? Y/N | Estimated Relocation Costs | Notice of Eligility Date delivered | Recevied Relocation Notice | Relocation Move-Out Date | Address of Relocation Space | Relocation Unit Inspection Date Completed | Estimated Term of Relocation | Received Re-Occupancy Notice | Date of Re-Occupancy | Moving Related Costs Requested & Reimbursed to Tenant (per regs for allowable incurred costs) | Date of Reimbursement to Tenant | Moving Related Costs Paid Directly by Owner | Date Moving Costs Paid by owner | Tenant Permanently relocated? Date? | Reason for Move
101 | Occupied | EXAMPLE | 2 BR/1BA/450 | 3 | 2021-01-01 | 2021-06-30 | 20000 | Y | Y | 650 | 50 | 700 | W/NH | 2021-05-01 | Hand Delivery | Y | Non displaced | Y | 500 | 2021-09-11 | 2021-09-11 | 2021-12-05 | 1234 Relocation Street, Bismarck | 2021-12-04 | 2 Months | 2022-02-01 | 2021-03-01 | 650 |  | 650 |  | NA | NA
102 | Vacant | - | [17 empty] | - | - | - | - |  | - | - | 2018-03-14
NOTES: EXAMPLE NOTES THAT CAN BE INCLUDED
Units #102 and #202 will be converted to ADA Type B accessible units.
Tenant Name (Unit #104) moved into Unit #102 upon re-occupancy for the accessibilty features.
Tenant Name (Unit #14) moved permanently to Unit #102 effective on the re-occupancy date.
Tenant Name (Unit #201) provided a notice to vacate on 3/9/2018 and opted not to move back to the property. Tenant was permanently relocated to Address